## Version History
Cognizant
Mainspring -
AVM PT Hand Book
Document Revision History
Ver # | Date | Prepared By | Revision Summary
V1.00 | 2016-03-10 | Envision - Process/Performance | Initial Version
V1.00-V1.14 | 2016-06-06 | Envision - Process/Performance | Updated the details in all sheets, based on review comments after BRD walkthough with config team
V1.15 | 2016-06-09 | Envision - Process/Performance | Updated based on the clarification tracker shared by Config team
V1.16 | 2016-06-15 | Envision - Process/Performance | Updated based on the review comments shared by Suresh BK
V1.17 | 2016-06-16 | Envision - Process/Performance | Removed Tailoring questions and updated to have all phases for Testing in Apllication Strengthening
V1.18 | 2016-06-28 | Suresh B. K. | Added the sheet "Order of Phases" where information of order of phases within each practice is provided
V1.19 | 2016-06-30 | Suresh B. K. | Removed the flags Test Driven Development and Application security
V1.20 | 2016-07-05 | Envision - Performance | Updates to the Testing Practice Activity Codes as per Suresh comments
V1.21 | 2017-12-08 | Vishu K | Updates to Activities in UAT phase for AS/RC. CSI related updated
V2.0 | 2017-12-20 | Aswini Murugavel | As per discussion with Suresh on 19-Dec-17, removed Project Management capability from MAS - PT mapping sheet. For Project Management phases & activities, do refer to "PDM Activity code for consolidated V2.2". In the Sharepoint link and navigate to Mainspring Repository-->Life Cycle Docs Repository-->Baselined-->01 Requirements-->R01 Common--> R1.18 Project Management PDT--> PDM Activity code for consolidated V2.2

## Quick Pivot (hidden)
Practice | Project Management
Row Labels | Count of Activity Code
Monitoring and Control | 16
Account Management Review | 1
Application Strengthening Monitoring and Control | 1
Change Management | 1
Coordination with Projects | 1
CSI Execute | 2
Defect Prevention Analysis | 1
Functional Enhancement Monitoring and Control | 1
Integrated Governance Discussions | 1
Monitoring and Control | 1
Project Management Review | 1
Quality and Audit Related Activities | 1
Quantitative Project Management | 1
Regulatory Compliance Monitoring and Control | 1
Risk Monitoring and Control | 1
Steering Committee Meeting | 1
Project Closure | 3
Project Closure Documentation | 1
Project Closure Meetings | 1
Project Closure Report | 1
Project Initiation | 2
Project Initiation | 1
Project Set up | 1
Project Planning | 24
BCM Planning | 1
CSI Plan sign off | 1
CSI Planning | 7
Develop Project Management Plan | 1
Independent Testing Plan | 1
Metrics and Goal Setting | 1
Project Estimation | 1
Project Planning | 7
Project Scheduling | 1
Review Project Management Plan | 1
Schedule Review | 1
Schedule Rework | 1
Grand Total | 45

## MAS - PT Mapping
Line No | Practice | Phase | Activity Code | List of Activities | COQ | Milestone | Mandatory | Predecessor | Flags | List of Deliverable (Optional) | Entry Criteria (Optional) | Exit Criteria (Optional) | Activity Role Mapping (Optional)
46 | Application Strengthening | Impact Analysis and Requirements | Requirements | Analyze And Identify The Problem | NA | No | Mandatory
47 | Application Strengthening | Impact Analysis and Requirements | Requirements | Assign Request | NA | No | Mandatory
48 | Application Strengthening | Impact Analysis and Requirements | Requirements | Create And Categorize Request | NA | No | Mandatory
49 | Application Strengthening | Impact Analysis and Requirements | Requirements | Identify Fragile And Vulnerable Areas In Application | NA | No | Optional
50 | Application Strengthening | Impact Analysis and Requirements | Requirements Review | Review of requirements | Appraisal | No | Mandatory
51 | Application Strengthening | Impact Analysis and Requirements | Requirements Rework | Rework of requirements | Failure | No | Mandatory
52 | Application Strengthening | Impact Analysis and Requirements | Requirements Approval | Obtain Approval From Change Control Board | NA | Yes | Mandatory
53 | Application Strengthening | Impact Analysis and Requirements | Requirements Concurrence | Obtain Concurrence On The Proposed Change | NA | No | Optional
54 | Application Strengthening | Impact Analysis and Requirements | Requirements Sign off | Requirements Sign Off | NA | Yes | Mandatory
55 | Application Strengthening | Impact Analysis and Requirements | Impact Analysis | Perform Impact Analysis | NA | No | Optional
56 | Application Strengthening | Impact Analysis and Requirements | Estimation | Prepare Detailed Estimation | NA | No | Optional
57 | Application Strengthening | Impact Analysis and Requirements | Timelines | Prepare Draft Timeline | NA | No | Optional
58 | Application Strengthening | Impact Analysis and Requirements | Estimation | Prepare Level 0 Estimate | NA | No | Mandatory
59 | Application Strengthening | Design | Traceability | Establish Overall Traceability For Application Strengthening | NA | No | Optional
60 | Application Strengthening | Design | Design | Design The Solution For requirement | NA | No | Optional
61 | Application Strengthening | Design | Design Review | Review Design Of Solution for requirement | Appraisal | No | Mandatory
62 | Application Strengthening | Design | Design Rework | Rework Design Of Solution For requirement | Failure | No | Mandatory
102 | Application Strengthening | Design | Unit Test Plan | Prepare Unit Test Scripts Or Cases For Application Strengthening Request | NA | No | Mandatory
103 | Application Strengthening | Design | Unit Test Plan Review | Review Unit Test Scripts Or Cases For Application Strengthening Request | Appraisal | No | Mandatory
104 | Application Strengthening | Design | Unit Test Plan Rework | Rework Unit Test Scripts Or Cases For Application Strengthening Request | Failure | No | Mandatory
106 | Application Strengthening | Design | System Test Plan | Prepare System Test Cases And Scripts For Application Strengthening Request | NA | No | Mandatory |  | NA for Independent testing
107 | Application Strengthening | Design | System Test Plan Review | Review System Test Cases for Application Strengthening Request | Appraisal | No | Mandatory |  | NA for Independent testing
108 | Application Strengthening | Design | System Test Plan Rework | Rework System Test Cases for Application Strengthening Request | Failure | No | Mandatory |  | NA for Independent testing
109 | Application Strengthening | Design | Regression Test Plan | Prepare Regression Test Cases And Scripts For Application Strengthening Request | NA | No | Optional |  | NA for Independent testing
110 | Application Strengthening | Design | Regression Test Plan Review | Review Regression Test Cases for Application Strengthening Request | Appraisal | No | Optional |  | NA for Independent testing
111 | Application Strengthening | Design | Regression Test Plan Rework | Rework Regression Test Cases for Application Strengthening Request | Failure | No | Optional |  | NA for Independent testing
112 | Application Strengthening | Design | Smoke Test Plan | Develop Smoke Test plan | NA | No | Optional |  | NA for Independent testing
113 | Application Strengthening | Design | Smoke Test Plan Review | Review Smoke Test plan | Appraisal | No | Optional |  | NA for Independent testing
114 | Application Strengthening | Design | Smoke Test Plan Rework | Rework Smoke Test plan | Failure | No | Optional |  | NA for Independent testing
66 | Application Strengthening | Design | Release Plan | Prepare Release Plan | NA | No | Optional
67 | Application Strengthening | Design | Design Sign off | Sign off design | NA | Yes | Mandatory
68 | Application Strengthening | Coding | Coding | Update Or Modify Code as per requirement | NA | No | Mandatory
69 | Application Strengthening | Coding | Code Review | Review Code as per requirement | Appraisal | No | Mandatory
70 | Application Strengthening | Coding | Code Rework | Rework Code as per requirement | Failure | No | Mandatory
71 | Application Strengthening | Coding | Code Sign off | Sign off code | NA | Yes | Mandatory
72 | Application Strengthening | Unit Testing | Unit Testing | Perform Unit Testing Of Code | Appraisal | No | Mandatory
73 | Application Strengthening | Unit Testing | Unit Test Rework | Fix Unit Testing Defects | Failure | No | Mandatory
74 | Application Strengthening | System Testing | Regression Testing | Perform Regression Testing | Appraisal | No | Optional |  | NA for Independent testing
75 | Application Strengthening | System Testing | Smoke Testing | Perform Smoke Testing | Appraisal | No | Optional |  | NA for Independent testing
76 | Application Strengthening | System Testing | Regression Testing Rework | Rework Regression Testing Defects Raised | Failure | No | Optional |  | NA for Independent testing
77 | Application Strengthening | System Testing | Smoke Testing Rework | Rework Smoke Testing Defects Raised | Failure | No | Optional |  | NA for Independent testing
78 | Application Strengthening | User Acceptance Testing | UAT | UAT | Appraisal | Yes | Mandatory
79 | Application Strengthening | Deployment | Build and Release | Acquire Necessary Approval For Release | NA | No | Mandatory
80 | Application Strengthening | Deployment | Build and Release | Create And Update Necessary Documentation | NA | No | Mandatory
81 | Application Strengthening | Deployment | Build and Release | Handover Support To Production Support Team | NA | No | Mandatory
82 | Application Strengthening | Deployment | Build and Release | Integrate Components And Create Build For Fix | NA | No | Mandatory
83 | Application Strengthening | Deployment | CSAT Survey | Conduct CSAT Survey | NA | No | Optional
84 | Application Strengthening | Deployment | Build and Release Sign Off | Obtain Business Sign off On The Implementation | NA | Yes | Mandatory
85 | Application Strengthening | Deployment | Build and Release | Perform Production Release Of The Updated Changes | NA | Yes | Mandatory
86 | Application Strengthening | Deployment | Build and Release | Perform Version Management | NA | No | Mandatory
87 | Functional Enhancements(Includes Bug Fixes) | Impact Analysis and Requirements | Requirements | Analyze Functional Enhancement Request | NA | No | Mandatory
88 | Functional Enhancements(Includes Bug Fixes) | Impact Analysis and Requirements | Requirements | Estimate Size Of Functional Enhancement Request | NA | No | Mandatory
89 | Functional Enhancements(Includes Bug Fixes) | Impact Analysis and Requirements | Requirements | Perform Impact Analysis Of Functional Enhancement | NA | No | Mandatory
90 | Functional Enhancements(Includes Bug Fixes) | Impact Analysis and Requirements | Requirements | Plan Functional Enhancement Request | NA | No | Mandatory
91 | Functional Enhancements(Includes Bug Fixes) | Impact Analysis and Requirements | Requirements | Prepare Detailed Schedule For Functional Enhancement | NA | No | Mandatory
92 | Functional Enhancements(Includes Bug Fixes) | Impact Analysis and Requirements | Requirements | Receive Functional Enhancement Request | NA | No | Mandatory
93 | Functional Enhancements(Includes Bug Fixes) | Impact Analysis and Requirements | Requirements Review | Review Functional Requirements | Appraisal | No | Mandatory
94 | Functional Enhancements(Includes Bug Fixes) | Impact Analysis and Requirements | Requirements Rework | Rework Functional Requirements | Failure | No | Mandatory
95 | Functional Enhancements(Includes Bug Fixes) | Impact Analysis and Requirements | Estimates Rework | Revisit Estimates Of Functional Enhancement Request | Failure | No | Mandatory
96 | Functional Enhancements(Includes Bug Fixes) | Impact Analysis and Requirements | Requirements Approval | SCCB Approval Of The Change And Impact | NA | No | Mandatory
97 | Functional Enhancements(Includes Bug Fixes) | Impact Analysis and Requirements | Requirements Sign off | Requirements Sign Off | NA | Yes | Mandatory
98 | Functional Enhancements(Includes Bug Fixes) | Design | Traceability | Establish Overall Traceability For Functional Enhancement | NA | No | Mandatory
99 | Functional Enhancements(Includes Bug Fixes) | Design | Design | Design The Solution For The Functional Enhancement Request | NA | No | Mandatory
100 | Functional Enhancements(Includes Bug Fixes) | Design | Design Review | Review Design Of Solution For Functional Enhancement Request | Appraisal | No | Mandatory
101 | Functional Enhancements(Includes Bug Fixes) | Design | Design Rework | Rework Design Of Solution For Functional Enhancement Request | Failure | No | Mandatory
102 | Functional Enhancements(Includes Bug Fixes) | Design | Unit Test Plan | Create Unit Test Scripts Or Cases For Functional Enhancement Request | NA | No | Mandatory
103 | Functional Enhancements(Includes Bug Fixes) | Design | Unit Test Plan Review | Review Unit Test Scripts Or Cases For Functional Enhancement Request | Appraisal | No | Mandatory
104 | Functional Enhancements(Includes Bug Fixes) | Design | Unit Test Plan Rework | Rework Unit Test Scripts Or Cases For Functional Enhancement Request | Failure | No | Mandatory
105 | Functional Enhancements(Includes Bug Fixes) | Design | NFR Test Plan | Develop NFR Test Cases Or Scripts | NA | No | Mandatory
106 | Functional Enhancements(Includes Bug Fixes) | Design | System Test Plan | Prepare or Update System Test Cases And Scripts For Functional Enhancement Request | NA | No | Mandatory |  | NA for Independent testing
107 | Functional Enhancements(Includes Bug Fixes) | Design | System and NFR Test Plan Review | Review System And NFR Test Cases | Appraisal | No | Mandatory
108 | Functional Enhancements(Includes Bug Fixes) | Design | System and NFR Test Plan Rework | Rework System And NFR Test Cases | Failure | No | Mandatory
109 | Functional Enhancements(Includes Bug Fixes) | Design | Regression Test Plan | Develop Regression Test plan | NA | No | Optional |  | NA for Independent testing
110 | Functional Enhancements(Includes Bug Fixes) | Design | Regression Test Plan Review | Review regression Test plan | Appraisal | No | Optional |  | NA for Independent testing
111 | Functional Enhancements(Includes Bug Fixes) | Design | Regression Test Plan Rework | Rework on regression Test plan | Failure | No | Optional |  | NA for Independent testing
112 | Functional Enhancements(Includes Bug Fixes) | Design | Smoke Test Plan | Develop Smoke Test plan | NA | No | Optional |  | NA for Independent testing
113 | Functional Enhancements(Includes Bug Fixes) | Design | Smoke Test Plan Review | Review Smoke Test plan | Appraisal | No | Optional |  | NA for Independent testing
114 | Functional Enhancements(Includes Bug Fixes) | Design | Smoke Test Plan Rework | Rework Smoke Test plan | Failure | No | Optional |  | NA for Independent testing
115 | Functional Enhancements(Includes Bug Fixes) | Design | Release Test Plan | Develop detailed Release Test plan | NA | No | Mandatory
116 | Functional Enhancements(Includes Bug Fixes) | Design | Design Sign off | Sign off design | NA | Yes | Mandatory
117 | Functional Enhancements(Includes Bug Fixes) | Coding | Coding | Update Or Modify Code To Fix Functional Enhancement Request | NA | No | Mandatory
118 | Functional Enhancements(Includes Bug Fixes) | Coding | Code Review | Review Code For Fixing Functional Enhancement Request | Appraisal | No | Mandatory
119 | Functional Enhancements(Includes Bug Fixes) | Coding | Code Rework | Rework Code For Fixing Functional Enhancement Request | Failure | No | Mandatory
120 | Functional Enhancements(Includes Bug Fixes) | Coding | Traceability Rework | Revisit Establish Overall Traceability | Failure | No | Mandatory
121 | Functional Enhancements(Includes Bug Fixes) | Unit Testing | Unit Testing | Perform Unit Testing Of Code For Fixing Functional Enhancement Request | Appraisal | No | Mandatory
122 | Functional Enhancements(Includes Bug Fixes) | Unit Testing | Unit Test Rework | Fix Unit Testing Defects For Functional Enhancement Request | Failure | No | Mandatory
123 | Functional Enhancements(Includes Bug Fixes) | System Testing | NFR Testing | Perform NFR Testing Of Code For Fixing Functional Enhancement Request | Appraisal | No | Mandatory
124 | Functional Enhancements(Includes Bug Fixes) | System Testing | NFR Testing Rework | Rework NFR Test Defects For Functional Enhancement To Closure | Failure | No | Mandatory
125 | Functional Enhancements(Includes Bug Fixes) | System Testing | System Testing | Perform System Testing Of Code For Fixing Functional Enhancement Request | Appraisal | No | Mandatory |  | NA for Independent testing
126 | Functional Enhancements(Includes Bug Fixes) | System Testing | System Testing Rework | Track System Testing Defects For Functional Enhancement To Closure | Failure | No | Mandatory
127 | Functional Enhancements(Includes Bug Fixes) | System Testing | Regression Testing | Perform Regression Testing Of Code For Fixing Functional Enhancement Request | Appraisal | No | Optional |  | NA for Independent testing
128 | Functional Enhancements(Includes Bug Fixes) | System Testing | Regression Testing Rework | Rework Regression Testing Defects Raised For Functional Enhancement Request | Failure | No | Optional
129 | Functional Enhancements(Includes Bug Fixes) | System Testing | Smoke Testing | Perform Smoke Testing For The Functional Enhancement Request | Appraisal | No | Optional
130 | Functional Enhancements(Includes Bug Fixes) | System Testing | Smoke Testing Rework | Rework Smoke Testing Defects Raised For Functional Enhancement Request | Failure | No | Optional
131 | Functional Enhancements(Includes Bug Fixes) | System Testing | System Test Summary | Prepare System Test Summary Report For Functional Enhancement | NA | No | Mandatory
132 | Functional Enhancements(Includes Bug Fixes) | System Testing | Build for UAT | Package And Deliver Resolution Of Functional Enhancement Request For User Acceptance Testing | NA | No | Mandatory
133 | Functional Enhancements(Includes Bug Fixes) | User Acceptance Testing | UAT Plan | Prepare or Update Acceptance Test Cases And Scripts For Functional Enhancement Request | NA | No | Mandatory
134 | Functional Enhancements(Includes Bug Fixes) | User Acceptance Testing | UAT Plan Review | Review Acceptance Test Cases And Scripts For Functional Enhancement Request | Appraisal | No | Mandatory
135 | Functional Enhancements(Includes Bug Fixes) | User Acceptance Testing | UAT Plan Rework | Rework Acceptance Test Cases And Scripts For Functional Enhancement Request | Failure | No | Mandatory
136 | Functional Enhancements(Includes Bug Fixes) | User Acceptance Testing | UAT | Perform User Acceptance Testing Of Resolution For Functional Enhancement Request | Appraisal | Yes | Mandatory
137 | Functional Enhancements(Includes Bug Fixes) | User Acceptance Testing | UAT Summary | Prepare UAT Test Summary Report For Functional Enhancement | NA | No | Mandatory
138 | Functional Enhancements(Includes Bug Fixes) | Deployment | Build and Release | Acquire Necessary Approval For Release | NA | Yes | Mandatory
139 | Functional Enhancements(Includes Bug Fixes) | Deployment | Build and Release | Create And Update Necessary Documentation | NA | No | Mandatory
140 | Functional Enhancements(Includes Bug Fixes) | Deployment | Build and Release | Perform Version Management | NA | No | Mandatory
141 | Functional Enhancements(Includes Bug Fixes) | Deployment | Build and Release | Integrate Components And Create Build For Fix | NA | No | Mandatory
142 | Functional Enhancements(Includes Bug Fixes) | Deployment | Build and Release | Handover Support To Production Support Team | NA | No | Mandatory
143 | Functional Enhancements(Includes Bug Fixes) | Deployment | Build and Release | Perform Production Release Of The Updated Changes | NA | No | Mandatory
144 | Functional Enhancements(Includes Bug Fixes) | Deployment | Deployment Sign off | Obtain Sign Off From Customer On Resolution For Functional Enhancement Request | NA | Yes | Mandatory
145 | Functional Enhancements(Includes Bug Fixes) | Deployment | Knowledge Transition | Conduct Knowledge Transition | NA | No | Mandatory
146 | Functional Enhancements(Includes Bug Fixes) | Deployment | CSAT Survey | Conduct CSAT Survey | NA | No | Optional
147 | Functional Enhancements(Includes Bug Fixes) | Deployment | Business Sign Off | Obtain Business Sign off On The Implementation | NA | Yes | Mandatory
148 | Regulatory Compliance | Impact Analysis and Requirements | Requirements | Assign Request | NA | No | Mandatory
149 | Regulatory Compliance | Impact Analysis and Requirements | Requirements | Obtain Approval Of The Change And Impact | NA | No | Mandatory
150 | Regulatory Compliance | Impact Analysis and Requirements | Requirements | Perform Impact Analysis | NA | No | Mandatory
151 | Regulatory Compliance | Impact Analysis and Requirements | Requirements | Perform Work Planning For The Changes | NA | No | Mandatory
152 | Regulatory Compliance | Impact Analysis and Requirements | Requirements | Prepare Detailed Estimation | NA | No | Mandatory
153 | Regulatory Compliance | Impact Analysis and Requirements | Requirements | Prepare Rough Order Magnitude Estimation | NA | No | Optional
154 | Regulatory Compliance | Impact Analysis and Requirements | Requirements | Re Prioritize The Request | NA | No | Optional
155 | Regulatory Compliance | Impact Analysis and Requirements | Requirements | Receive and Prioritize Regulatory Change Request From Customer | NA | No | Optional
156 | Regulatory Compliance | Impact Analysis and Requirements | Requirements Review | Review And Walk Through The BRD | Appraisal | No | Optional
157 | Regulatory Compliance | Impact Analysis and Requirements | Requirements Rework | Rework And Walk Through The BRD | Failure | No | Optional
158 | Regulatory Compliance | Impact Analysis and Requirements | Requirements Sign off | Requirements Sign Off | NA | Yes | Mandatory
159 | Regulatory Compliance | Design | Traceability | Establish Overall Traceability For Regulatory Compliance | NA | No | Mandatory
160 | Regulatory Compliance | Design | Design | Design The Solution For the Regulatory Compliance Request | NA | No | Mandatory
161 | Regulatory Compliance | Design | Design Review | Review Design Of Solution For Regulatory Compliance Request | Appraisal | No | Mandatory
162 | Regulatory Compliance | Design | Design Rework | Rework Design Of Solution For Regulatory Compliance Request | Failure | No | Mandatory
163 | Regulatory Compliance | Design | Unit Test Plan | Develop Unit test plan | NA | No | Mandatory
164 | Regulatory Compliance | Design | Unit Test Plan Review | Review Unit test plan | Appraisal | No | Mandatory
165 | Regulatory Compliance | Design | Unit Test Plan Rework | Rework Unit test plan | Failure | No | Mandatory
166 | Regulatory Compliance | Design | System Test Plan | Prepare Detailed System Test Plan | NA | No | Mandatory |  | NA for Independent testing
167 | Regulatory Compliance | Design | System Test Plan Review | Review System Test Plan | Appraisal | No | Mandatory |  | NA for Independent testing
168 | Regulatory Compliance | Design | System Test Plan Rework | Rework System Test Plan | Failure | No | Mandatory |  | NA for Independent testing
169 | Regulatory Compliance | Design | Regression Test Plan | Prepare Regression Test Plan | NA | No | Optional |  | NA for Independent testing
170 | Regulatory Compliance | Design | Regression Test Plan Review | Review Regression test plan | Appraisal | No | Optional |  | NA for Independent testing
171 | Regulatory Compliance | Design | Regression Test Plan Rework | Rework Regression Test Plan | Failure | No | Optional |  | NA for Independent testing
172 | Regulatory Compliance | Design | Smoke Test Plan | Prepare Smoke test plan | NA | No | Optional |  | NA for Independent testing
173 | Regulatory Compliance | Design | Smoke Test Plan Review | Review Smoke test plan | Appraisal | No | Optional
174 | Regulatory Compliance | Design | Smoke Test Plan Rework | Rework Smoke Test Plan | Failure | No | Optional |  | NA for Independent testing
175 | Regulatory Compliance | Design | Release Test Plan | Prepare detailed Release test plan | NA | No | Mandatory |  | NA for Independent testing
176 | Regulatory Compliance | Design | Design Sign off | Sign off design | NA | Yes | Mandatory
177 | Regulatory Compliance | Coding | Coding | Develop code | NA | No | Mandatory
178 | Regulatory Compliance | Coding | Code Review | Review Code For requirement | Appraisal | No | Mandatory
179 | Regulatory Compliance | Coding | Code Rework | Rework Code for requirement | Failure | No | Mandatory
180 | Regulatory Compliance | Coding | Traceability Rework | Revisit Establish Overall Traceability | Failure | No | Mandatory
181 | Regulatory Compliance | Unit Testing | Unit Testing | Perform Unit Testing Of Code | Appraisal | No | Mandatory |  | NA for Independent testing
182 | Regulatory Compliance | Unit Testing | Unit Test Rework | Fix Unit Testing Defects | Failure | No | Mandatory |  | NA for Independent testing
183 | Regulatory Compliance | System Testing | Regression Testing | Perform Regression Testing | Appraisal | No | Optional |  | NA for Independent testing
184 | Regulatory Compliance | System Testing | Regression Testing Rework | Rework Regression Testing Defects Raised | Failure | No | Optional |  | NA for Independent testing
185 | Regulatory Compliance | System Testing | Smoke Testing | Perform Smoke Testing | Appraisal | No | Optional |  | NA for Independent testing
186 | Regulatory Compliance | System Testing | Smoke Testing Rework | Rework Smoke Testing Defects Raised | Failure | No | Optional |  | NA for Independent testing
187 | Regulatory Compliance | System Testing | System Testing | Perform System Testing | Appraisal | No | Mandatory |  | NA for Independent testing
188 | Regulatory Compliance | System Testing | System Testing Rework | Rework System Testing Defects Raised | Failure | No | Mandatory |  | NA for Independent testing
189 | Regulatory Compliance | User Acceptance Testing | UAT | UAT | Appraisal | Yes | Mandatory
190 | Regulatory Compliance | User Acceptance Testing | UAT Sign off | UAT Business Sign off | NA | Yes | Mandatory
191 | Regulatory Compliance | Deployment | Build and Release | Integrate Components And Create Build For The Fix | NA | No | Mandatory
192 | Regulatory Compliance | Deployment | Build and Release | Acquire Necessary Approval For Release | NA | No | Mandatory
193 | Regulatory Compliance | Deployment | Build and Release | Create And Update Necessary Documentation | NA | No | Mandatory
194 | Regulatory Compliance | Deployment | Build and Release | Perform Version Management | NA | No | Mandatory
195 | Regulatory Compliance | Deployment | Build and Release | Perform Production Release Of The Updated Changes | NA | No | Mandatory
196 | Regulatory Compliance | Deployment | Build and Release | Prepare and Maintain Forms And Documents | NA | No | Mandatory
197 | Regulatory Compliance | Deployment | Build and Release | Handover Support To Production Support Team | NA | No | Mandatory
198 | Regulatory Compliance | Deployment | Warranty Support | Perform Warranty Support For The Agreed Period | Failure | No | Mandatory
199 | Regulatory Compliance | Deployment | CSAT Survey | Conduct CSAT Survey | NA | No | Optional
200 | Regulatory Compliance | Deployment | Business Sign off | Obtain Business Sign off On The Implementation | NA | Yes | Mandatory
201 | Regulatory Compliance | Deployment | Sign off Production Release | Sign off Production Release | NA | Yes | Mandatory
202 | Knowledge Transition | Knowledge Transition Planning | Planning Requirements | Identify and confirm scope or objective | NA | No | Mandatory |  | Co Managed and MS
203 | Knowledge Transition | Knowledge Transition Planning | Planning Requirements | Align and Study current set up | NA | No | Mandatory |  | Co Managed and MS
204 | Knowledge Transition | Knowledge Transition Planning | Planning Requirements | Identify and block SME calendars or KT | NA | No | Mandatory |  | Co Managed and MS
205 | Knowledge Transition | Knowledge Transition Planning | Planning Requirements | Create and schedule KT plan | NA | No | Mandatory |  | Co Managed and MS
206 | Knowledge Transition | Knowledge Transition Planning | Planning Requirements | Prepare and finalize KT templates | NA | No | Mandatory |  | Co Managed and MS
207 | Knowledge Transition | Knowledge Transition Planning | Planning Requirements | Creation of Detailed project plan and sign off | NA | No | Mandatory |  | Co Managed and MS
208 | Knowledge Transition | Knowledge Transition Planning | Planning Requirements | Identify Risks or mitigation plan for each | NA | No | Mandatory |  | Co Managed and MS
209 | Knowledge Transition | Knowledge Transition Planning | Planning Requirements | Creation of Infra readiness plan | NA | No | Mandatory |  | Co Managed and MS
210 | Knowledge Transition | Knowledge Transition Planning | Readiness Sign off | Firm up KT Readiness Checklist and sign off | NA | Yes | Mandatory |  | Co Managed and MS
211 | Knowledge Transition | Knowledge Transition Planning | Performance tracker Sign off | Identify KT Performance Tracker and sign off | NA | Yes | Mandatory |  | Co Managed and MS
212 | Knowledge Transition | Pre KT | Training | Business Unit Overview | NA | No | Mandatory |  | Co Managed and MS
213 | Knowledge Transition | Pre KT | Training | Alignment of IT Business | NA | No | Mandatory |  | Co Managed and MS
214 | Knowledge Transition | Pre KT | Training | Capture the expectations from client and sign off | NA | No | Mandatory |  | Co Managed and MS
215 | Knowledge Transition | Pre KT | Training | Analyze the data and identify seasonal variations and peak demand etc. | NA | No | Mandatory |  | Co Managed and MS
216 | Knowledge Transition | Pre KT | Training | Create detailed documentation and sign off | NA | No | Mandatory |  | Co Managed and MS
217 | Knowledge Transition | Pre KT | Training | Update KR portal with all details | NA | No | Mandatory |  | Co Managed and MS
218 | Knowledge Transition | Pre KT | Reverse KT | Update reverse KT plan and sign off | NA | Yes | Mandatory |  | Co Managed and MS
219 | Knowledge Transition | Knowledge Acquisition | Acquisition | Gather knowledge from incumbent teams | NA | No | Mandatory |  | Co Managed and MS
220 | Knowledge Transition | Knowledge Acquisition | Acquisition | Understand systems and technology landscape and and support processes | NA | No | Mandatory |  | Co Managed and MS
221 | Knowledge Transition | Knowledge Acquisition | Baseline SLA | Discuss SLA s and sign off s | NA | No | Mandatory |  | Co Managed and MS
222 | Knowledge Transition | Knowledge Acquisition | Training Documentation | Prepare exhaustive KT documentation | NA | No | Mandatory |  | Co Managed and MS
223 | Knowledge Transition | Knowledge Acquisition | Enhance Knowledge Repository | Update KR portal with all details | NA | No | Mandatory |  | Co Managed and MS
224 | Knowledge Transition | Knowledge Acquisition | Training Documents Sign off | Create detailed documentation and sign off | NA | Yes | Mandatory |  | Co Managed and MS
225 | Knowledge Transition | Knowledge Acquisition | Reverse KT Sign off | Update reverse KT plan and sign off | NA | Yes | Mandatory |  | Co Managed and MS
226 | Knowledge Transition | Knowledge Acquisition | Acquisition Sign off | Update and review KT Effectiveness scorecard | NA | Yes | Mandatory |  | Co Managed and MS
227 | Knowledge Transition | Knowledge Acquisition | Phase Exit Sign off | Seek sign off on KT phase exit | NA | Yes | Mandatory |  | Co Managed and MS
228 | Knowledge Transition | Shadow Support | Secondary Support | Observe and monitor incumbent support team | NA | No | Mandatory |  | Co Managed and MS
229 | Knowledge Transition | Shadow Support | Secondary Support | Complete training of offshore support teams | NA | No | Mandatory |  | Co Managed and MS
230 | Knowledge Transition | Shadow Support | Secondary Support | Resolve high priority incidents along with teams | NA | No | Mandatory |  | Co Managed and MS
231 | Knowledge Transition | Shadow Support | Secondary Support | Refine run books and documentation and publish | NA | No | Mandatory |  | Co Managed and MS
232 | Knowledge Transition | Shadow Support | Document Sign off | Sign off on run books and manuals and reporting templates | NA | Yes | Mandatory |  | Co Managed and MS
233 | Knowledge Transition | Shadow Support | Secondary Support | Update process and technical SOPs | NA | No | Mandatory |  | Co Managed and MS
234 | Knowledge Transition | Shadow Support | Secondary Support | Create detailed escalation plan | NA | No | Mandatory |  | Co Managed and MS
235 | Knowledge Transition | Shadow Support | Secondary Support | Sign off Transition exit with customer | NA | Yes | Mandatory |  | Co Managed and MS
236 | Knowledge Transition | Shadow Support | Secondary Support | Finalize and report metrics or SLAs | NA | No | Mandatory |  | Co Managed and MS
237 | Knowledge Transition | Reverse Shadow | Primary Support | Resources start providing support independently from offshore | NA | No | Mandatory |  | Co Managed and MS
238 | Knowledge Transition | Reverse Shadow | Primary Support | Assume primary support | NA | No | Mandatory |  | Co Managed and MS
239 | Knowledge Transition | Reverse Shadow | Primary Support | Initiate handling critical tasks | NA | No | Mandatory |  | Co Managed and MS
240 | Knowledge Transition | Reverse Shadow | Primary Support | Capture and report current SLAs in the phase | NA | No | Mandatory |  | Co Managed and MS
241 | Testing | Test Strategy and Planning | Test Requirements | Understand business processor intended application | NA | No | Optional
242 | Testing | Test Strategy and Planning | Test Requirements | Prepare application inventory | NA | No | Optional
243 | Testing | Test Strategy and Planning | Test Requirements | Elicit and analyze test requirements | NA | No | Optional
244 | Testing | Test Strategy and Planning | Test Requirements Traceability | Establish test requirements traceability | NA | No | Optional
245 | Testing | Test Strategy and Planning | Test Requirements | Document test requirements | NA | No | Optional
246 | Testing | Test Strategy and Planning | Test Requirements Review | Review test requirements | Appraisal | No | Optional
247 | Testing | Test Strategy and Planning | Test Requirements Rework | Rework test requirements | Failure | No | Optional
248 | Testing | Test Strategy and Planning | Test Strategy | Develop Test strategy for integration and system regression | NA | No | Optional
249 | Testing | Test Strategy and Planning | Test Strategy Review | Review Test strategy | Appraisal | No | Optional
250 | Testing | Test Strategy and Planning | Test Strategy Rework | Rework Test strategy | Failure | No | Optional
251 | Testing | Test Strategy and Planning | Acceptance Test Strategy | Develop Test strategy for user acceptance testing | NA | No | Mandatory
252 | Testing | Test Strategy and Planning | Acceptance Test Plan | Develop Acceptance Test Cases | Appraisal | No | Optional
253 | Testing | Test Strategy and Planning | Acceptance Test Plan Review | Review Acceptance Test Cases | Appraisal | No | Optional
254 | Testing | Test Strategy and Planning | Acceptance Test Plan Rework | Rework Acceptance Test Cases | Failure | No | Optional
255 | Testing | Test Strategy and Planning | Test Requirements Sign off | Sign off test requirements | NA | Yes | Mandatory
256 | Testing | Test Design | Integration Test Plan | Develop Integration Test plans and scenarios and cases | NA | No | Optional
257 | Testing | Test Design | Integration Test Plan Review | Review Integration Test plans and scenarios and cases | Appraisal | No | Optional
258 | Testing | Test Design | Integration Test Plan Rework | Rework Integration Test plans and scenarios and cases | Failure | No | Optional
259 | Testing | Test Design | Integration Test Plan Sign Off | Sign off integration test plans and scenarios and test cases | NA | Yes | Mandatory
260 | Testing | Test Design | System Test Plan | Develop system Test plans and scenarios and cases | NA | No | Optional
261 | Testing | Test Design | System Test Plan Review | Review system Test plans and scenarios and cases | Appraisal | No | Optional
262 | Testing | Test Design | System Test Plan Rework | Rework system Test plans and scenarios and cases | Failure | No | Optional
263 | Testing | Test Design | System Test Plan Sign Off | Sign off system test plans and scenarios and test cases | NA | Yes | Mandatory
264 | Testing | Test Design | Regression Test Plan | Develop regression Test suites and cases | Appraisal | No | Optional
265 | Testing | Test Design | Regression Test Plan Review | Review regression Test suites and cases | Appraisal | No | Optional
266 | Testing | Test Design | Regression Test Plan Rework | Rework regression Test suites and cases | Failure | No | Optional
267 | Testing | Test Design | Regression Test Plan Sign Off | Sign off regression test suites and test cases | NA | Yes | Mandatory
268 | Testing | Test Design | Traceability Test Cases | Establish traceability of system or integration or regression test cases | NA | No | Optional
269 | Testing | Test Design | Test Data Requirements | Prepare test data requirements | NA | No | Optional
270 | Testing | Test Design | Test Data Review | Review test data | Appraisal | No | Optional
271 | Testing | Test Design | Test Data Rework | Rework test data | Failure | No | Optional
272 | Testing | Test Design | Test Environment Setup | Configure test environment | NA | No | Optional
273 | Testing | Test Execution | Application Performance | Compile application performance baselines | NA | No | Optional
274 | Testing | Test Execution | Smoke Testing | Perform smoke testing | Appraisal | No | Optional
275 | Testing | Test Execution | Integration Testing | Perform integration testing | Appraisal | No | Optional
276 | Testing | Test Execution | System Testing | Perform system testing | Appraisal | No | Optional
277 | Testing | Test Execution | Regression Testing | Perform regression testing | Appraisal | No | Optional
278 | Testing | Test Execution | Test Reporting Summary | Prepare test summary report | NA | No | Optional
279 | Testing | Test Execution | System Testing Rework | Resolve defects | Failure | No | Optional
280 | Testing | Test Execution | System Test Sign off | Sign off testing | NA | No | Optional
281 | Testing | User Acceptance Testing | UAT Data Setup | Setup and verify UAT Test data | NA | No | Optional
282 | Testing | User Acceptance Testing | UAT Test Environment Setup | Setup acceptance test environment | NA | No | Optional
283 | Testing | User Acceptance Testing | User Acceptance Testing | Perform UAT | Appraisal | No | Optional
284 | Testing | User Acceptance Testing | User Acceptance Testing Rework | Resolve UAT Defects | Failure | No | Optional
285 | Testing | User Acceptance Testing | User Acceptance Testing Sign Off | UAT Sign Off | NA | Yes | Mandatory
286 | Continual Service Improvement | Project Planning | CSI Planning | Determine CSI Requirements | NA | No | Mandatory
287 | Continual Service Improvement | Project Planning | CSI Planning | Identify CSI Core Team | NA | No | Mandatory
288 | Continual Service Improvement | Project Planning | CSI Planning | Identify Themes To Address Pain Areas Or Opportunities | NA | No | Mandatory
289 | Continual Service Improvement | Project Planning | CSI Planning | Review And Approve Themes By Key Stakeholders And Customer | Appraisal | No | Mandatory
290 | Continual Service Improvement | Project Planning | CSI Planning | Identify Solution Approach | NA | No | Mandatory
291 | Continual Service Improvement | Project Planning | CSI Planning | Create CSI Execution Plan | NA | No | Mandatory
292 | Continual Service Improvement | Project Planning | CSI Planning | Review And Approve CSI Execution Plan | Appraisal | No | Mandatory
293 | Continual Service Improvement | Project Planning | CSI Plan sign off | CSI Plan Sign Off | NA | No | Mandatory
294 | Continual Service Improvement | Monitoring & Control | CSI Execute | Execute CSI Plan | NA | No | Mandatory
295 | Continual Service Improvement | Monitoring & Control | CSI Execute | Review And Approve CSI Executed Plan | Appraisal | No | Mandatory

## Order of Phases
Practice | Phase | Order
Project Management | Project Initiation | 1
Project Management | Project Planning | 2
Project Management | Monitoring and Control | 3
Project Management | Project Closure | 4
Application Strengthening | Impact Analysis and Requirements | 1
Application Strengthening | Design | 2
Application Strengthening | Coding | 3
Application Strengthening | Unit Testing | 4
Application Strengthening | System Testing | 5
Application Strengthening | User Acceptance Testing | 6
Application Strengthening | Deployment | 7
Functional Enhancements(Includes Bug Fixes) | Impact Analysis and Requirements | 1
Functional Enhancements(Includes Bug Fixes) | Design | 2
Functional Enhancements(Includes Bug Fixes) | Coding | 3
Functional Enhancements(Includes Bug Fixes) | Unit Testing | 4
Functional Enhancements(Includes Bug Fixes) | System Testing | 5
Functional Enhancements(Includes Bug Fixes) | User Acceptance Testing | 6
Functional Enhancements(Includes Bug Fixes) | Deployment | 7
Regulatory Compliance | Impact Analysis and Requirements | 1
Regulatory Compliance | Design | 2
Regulatory Compliance | Coding | 3
Regulatory Compliance | Unit Testing | 4
Regulatory Compliance | System Testing | 5
Regulatory Compliance | User Acceptance Testing | 6
Regulatory Compliance | Deployment | 7
Knowledge Transition | Knowledge Transition Planning | 1
Knowledge Transition | Pre KT | 2
Knowledge Transition | Knowledge Acquisition | 3
Knowledge Transition | Shadow Support | 4
Knowledge Transition | Reverse Shadow | 5
Testing | Test Strategy and Planning | 1
Testing | Test Design | 2
Testing | Test Execution | 3
Testing | User Acceptance Testing | 4

## AD-Waterfall (hidden)
Line No | Practice | Phase | Activity Code | List of Activities | COQ | Milestone | Mandatory | Predecessor | Flags | List of Deliverable (Optional) | Entry Criteria (Optional) | Exit Criteria (Optional) | Activity Role Mapping (Optional)
1 | AD-Waterfall | Requirements | Functional Requirements | Analyze & Develop Requirement | NA | No | Mandatory |  |  | <Phase Level> | <Phase Level> | <Phase Level>
2 | AD-Waterfall | Requirements | Functional Requirements | Determine application quality quantitatively and establish their goals | NA | No | Optional
3 | AD-Waterfall | Requirements | Functional Requirements | Establish bidirectional traceability matrix | NA | No | Mandatory
4 | AD-Waterfall | Requirements | Functional Requirements Sign off | Requirements Sign-Off | NA | Yes | Mandatory
5 | AD-Waterfall | Requirements | Functional Requirements | Establish design standards | NA | No | Optional
6 | AD-Waterfall | Requirements | Functional Requirements | Establish coding standards | NA | No | Optional
7 | AD-Waterfall | Requirements | Functional Requirements | Provide necessary knowledge transition to the Independent testing team | NA | No | Optional
8 | AD-Waterfall | Requirements | Functional Requirements | Plan and conduct knowledge transtion | NA | No | Optional |  | Test Driven Development
9 | AD-Waterfall | Requirements | Functional Requirements | Prepare requirements traceability matrix & heat maps | NA | No | Optional |  | Test Driven Development
10 | AD-Waterfall | Requirements | Functional Requirements | Perform requirements testing, business process verification and identification of requirements defects | NA | No | Optional |  | Test Driven Development
11 | AD-Waterfall | Requirements | Functional Requirements | Determine data security requirements | NA | No | Optional |  | Application Security
12 | AD-Waterfall | Requirements | Functional Requirements | Determine identity and access management requirements | NA | No | Optional |  | Application Security
13 | AD-Waterfall | Requirements | Functional Requirements | Brainstrom and create user journeys | NA | No | Optional |  | User Experience
14 | AD-Waterfall | Requirements | Functional Requirements | Perform current state diagnotics | NA | No | Optional |  | Business Process Transformation
15 | AD-Waterfall | Requirements | Functional Requirements | Perform gap analysis and target state design | NA | No | Optional |  | Business Process Transformation
16 | AD-Waterfall | Requirements | Functional Requirements | Provide roadmap & recommendations | NA | No | Optional |  | Business Process Transformation
17 | AD-Waterfall | Requirements | Non Functional Requirements | Gather NFR | NA | No | Optional
18 | AD-Waterfall | Requirements | Non Functional Requirements | Prepare Non Functional Requirement Document | NA | No | Optional
19 | AD-Waterfall | Requirements | Non Functional Requirements | Prepare NFR Traceability Matrix | NA | No | Optional
20 | AD-Waterfall | Requirements | Non Functional Requirements | Determine data security requirements | NA | No | Optional
21 | AD-Waterfall | Requirements | Non Functional Requirements | Determine identity and access management requirements | NA | No | Optional
22 | AD-Waterfall | Requirements | Requirements Review | Requirements Review | Appraisal | No | Mandatory
23 | AD-Waterfall | Requirements | Requirements Review | Review and analyze the business requirements | Appraisal | No | Mandatory |  | Test Driven Development
24 | AD-Waterfall | Requirements | Requirements Review | Verify requirements traceability matrix | Appraisal | No | Mandatory |  | Test Driven Development
25 | AD-Waterfall | Requirements | Requirements Rework | Requirements Rework | Failure | No | Mandatory
26 | AD-Waterfall | Requirements | Prototype Development | Create feature roadmap, concept prototype and wireframe | NA | No | Optional |  | User Experience
27 | AD-Waterfall | Requirements | Prototype Review | Validate UX prototype | Appraisal | No | Optional |  | User Experience
28 | AD-Waterfall | Requirements | Prototype Development | Baseline UX standards | NA | No | Optional |  | User Experience
29 | AD-Waterfall | Requirements | UAT Plan | Develop Acceptance Test strategy and Cases | Appraisal | No | Mandatory |  | NA for Independent testing
30 | AD-Waterfall | Requirements | UAT Plan Review | Review Acceptance Test strategy and Cases | Appraisal | No | Mandatory |  | NA for Independent testing
31 | AD-Waterfall | Requirements | UAT Plan Rework | Rework Acceptance Test strategy and Cases | Failure | No | Mandatory |  | NA for Independent testing
32 | AD-Waterfall | Requirements | System Test Plan | Develop System/Integration Test strategy and cases | Appraisal | No | Mandatory
33 | AD-Waterfall | Requirements | System Test Plan | Prepare test strategy, scope and test plans | Appraisal | No | Mandatory |  | Test Driven Development
34 | AD-Waterfall | Requirements | System Test Plan Sign off | Sign off system/ integration test strategy and test cases | NA | No | Mandatory
35 | AD-Waterfall | Requirements | System Test Plan | Establish traceability of system/ integration test cases | Appraisal | No | Mandatory |  | NA for Independent testing
36 | AD-Waterfall | Requirements | System Test Plan Review | Review System/Integration Test strategy and cases | Appraisal | No | Mandatory
37 | AD-Waterfall | Requirements | System Test Plan Rework | Rework System/Integration Test strategy and cases | Failure | No | Mandatory |  | NA for Independent testing
38 | AD-Waterfall | Requirements | System Test Plan Rework | Rework system Test plans, scenarios and cases | Failure | No | Mandatory
39 | AD-Waterfall | Architecture | Architecture | Develop architecture | NA | No | Mandatory
40 | AD-Waterfall | Architecture | Architecture | Develop architecture considering identity and access management requirements | NA | No | Optional |  | Application Security
41 | AD-Waterfall | Architecture | Architecture Review | Validate UX considerations in architecture | Appraisal | No | Optional |  | User Experience
42 | AD-Waterfall | Architecture | Architecture Sign off | Signoff architecture | NA | Yes | Mandatory
43 | AD-Waterfall | Architecture | Architecture Review | Review architecture | Appraisal | No | Mandatory
44 | AD-Waterfall | Architecture | Architecture Rework | Rework architecture | Failure | No | Mandatory
45 | AD-Waterfall | Design | Design | Establish design standards | NA | No | Optional
46 | AD-Waterfall | Design | Capacity Planning | Prepare capacity plan | NA | No | Optional
47 | AD-Waterfall | Design | Design | Develop design | NA | No | Mandatory
48 | AD-Waterfall | Design | Develop Design Environment | Set up development environment | NA | No | Optional |  | NA for Independent testing
49 | AD-Waterfall | Design | Design | Establish design traceability | NA | No | Mandatory
50 | AD-Waterfall | Design | Design | Develop data masking process design | NA | No | Optional |  | Application Security
51 | AD-Waterfall | Design | Design | Develop identity and access management process design | NA | No | Optional |  | Application Security
52 | AD-Waterfall | Design | Design | Develop threat models | NA | No | Optional |  | Application Security
53 | AD-Waterfall | Design | Design Test Strategy | Determine unit test strategy | Appraisal | No | Mandatory
54 | AD-Waterfall | Design | Design Sign off | Sign off design | NA | Yes | Mandatory
55 | AD-Waterfall | Design | Design Review | Design Review | Appraisal | No | Mandatory
56 | AD-Waterfall | Design | Design Review | Validate UX considerations in design | Appraisal | No | Optional |  | User Experience
57 | AD-Waterfall | Design | Design Rework | Design Rework | Failure | No | Mandatory
58 | AD-Waterfall | Design | Integration Test Plan | Create test scenarios and test cases - Functional, Automation & NFT | Appraisal | No | Optional |  | Test Driven Development
59 | AD-Waterfall | Design | Integration Test Plan | Prepare module specific test suites | Appraisal | No | Optional |  | Test Driven Development
60 | AD-Waterfall | Design | Integration Test Plan | Map requirements to test suites | Appraisal | No | Optional |  | Test Driven Development
61 | AD-Waterfall | Design | Integration Test Plan | Implement defect prediction model | Appraisal | No | Optional |  | Test Driven Development
62 | AD-Waterfall | Design | Integration Test Plan Review | Review of Integration Test Plan | Appraisal | No | Mandatory
63 | AD-Waterfall | Design | Integration Test Plan Rework | Rework Integration Test strategy and cases | Failure | No | Mandatory
64 | AD-Waterfall | Design | Integration Test Plan Rework | Rework Integration Test plans, scenarios and cases | Failure | No | Mandatory
65 | AD-Waterfall | Coding and Unit Testing | Coding | Perform coding | NA | No | Mandatory
66 | AD-Waterfall | Coding and Unit Testing | Coding | Perform code profiling and code assessment | NA | No | Mandatory |  | Test Driven Development
67 | AD-Waterfall | Coding and Unit Testing | Coding | Establish traceability of code | NA | No | Mandatory
68 | AD-Waterfall | Coding and Unit Testing | Code Profiling and Coverage Analysis | Perform code profiling & code coverage analysis | NA | No | Mandatory
69 | AD-Waterfall | Coding and Unit Testing | Develop Code and Unit Testing Environment | Configure data masking tools in development environment | NA | No | Optional |  | Application Security
70 | AD-Waterfall | Coding and Unit Testing | Coding | Configure identity and access management components | NA | No | Optional |  | Application Security
71 | AD-Waterfall | Coding and Unit Testing | Code Sign off | Sign off code | NA | Yes | Mandatory
72 | AD-Waterfall | Coding and Unit Testing | Compile Build | Compile Build | NA | No | Mandatory
73 | AD-Waterfall | Coding and Unit Testing | Code Review | Review code | Appraisal | No | Mandatory
74 | AD-Waterfall | Coding and Unit Testing | Code Review | Perform continuous inspection of code quality of application | Appraisal | No | Mandatory
75 | AD-Waterfall | Coding and Unit Testing | Code Review | Validate environment readiness | Appraisal | No | Mandatory |  | Test Driven Development
76 | AD-Waterfall | Coding and Unit Testing | Code Review | Review code with respect to threat model | Appraisal | No | Optional |  | Application Security
77 | AD-Waterfall | Coding and Unit Testing | Code Review | Test data preparation & set up | Appraisal | No | Mandatory |  | Test Driven Development
78 | AD-Waterfall | Coding and Unit Testing | Code Review | Perform White box testing & review unit test logs | Appraisal | No | Mandatory |  | Test Driven Development
79 | AD-Waterfall | Coding and Unit Testing | Set up Code and Unit Testing Environment | Set up test environment | NA | No | Optional
80 | AD-Waterfall | Coding and Unit Testing | Unit Test Planning | Develop Unit Test plan and Cases | Appraisal | No | Mandatory
81 | AD-Waterfall | Coding and Unit Testing | Unit Testing | Perform Unit Testing | Appraisal | No | Mandatory
82 | AD-Waterfall | Coding and Unit Testing | Data Set up for IT and ST | Prepare test data for integration, system and performance testing | NA | No | Mandatory |  | NA for Independent testing
83 | AD-Waterfall | Coding and Unit Testing | Unit Test Planning | Develop Unit Test plan and Cases | NA | No | Mandatory
84 | AD-Waterfall | Coding and Unit Testing | UTP Review | Review Unit Test plan and Cases | Appraisal | No | Mandatory
85 | AD-Waterfall | Coding and Unit Testing | UTP Rework | Rework Unit Test plan and Cases | Failure | No | Mandatory
86 | AD-Waterfall | Validation | Integration Testing | Perform smoke testing | Appraisal | No | Mandatory |  | NA for Independent testing
87 | AD-Waterfall | Validation | Integration Testing | Execute test cases and suites | Appraisal | No | Mandatory
88 | AD-Waterfall | Validation | Integration Testing | Execute end to end test scenarios | Appraisal | No | Mandatory
89 | AD-Waterfall | Validation | Integration Testing | Perform integration testing | Appraisal | No | Mandatory |  | NA for Independent testing
90 | AD-Waterfall | Validation | Integration Testing | Perform continuous integration testing with applications | Appraisal | No | Mandatory
91 | AD-Waterfall | Validation | System Testing | Perform system testing | Appraisal | No | Mandatory |  | NA for Independent testing
92 | AD-Waterfall | Validation | System Testing | Execute test cases and suites | Appraisal | No | Mandatory
93 | AD-Waterfall | Validation | System Testing | Execute end to end test scenarios | Appraisal | No | Mandatory
94 | AD-Waterfall | Validation | System Testing Sign off | Sign off testing | NA | Yes | Mandatory
95 | AD-Waterfall | Validation | System Testing | Perform regression testing (NA for Independent testing) | Appraisal | No | Mandatory |  | NA for Independent testing
96 | AD-Waterfall | Validation | End to End Testing | Perform vulnerability assessment and testing of security considerations | Appraisal | No | Mandatory |  | Application Security
97 | AD-Waterfall | Validation | System Testing | Prepare test summary report | Appraisal | No | Mandatory |  | NA for Independent testing
98 | AD-Waterfall | Validation | Integration Testing Rework | Resolve defects | Failure | No | Mandatory
99 | AD-Waterfall | Validation | System Testing Rework | Resolve defects | Failure | No | Mandatory
100 | AD-Waterfall | Validation | End to End Testing | Perform static & dynamic analysis | Appraisal | No | Mandatory |  | Test Driven Development
101 | AD-Waterfall | Validation | End to End Testing | Execute test cases and suites | Appraisal | No | Mandatory |  | Test Driven Development
102 | AD-Waterfall | Validation | End to End Testing | Perform continuous integration testing with applications | Appraisal | No | Mandatory |  | Test Driven Development
103 | AD-Waterfall | Validation | End to End Testing | Execute end to end test scenarios | Appraisal | No | Mandatory |  | Test Driven Development
104 | AD-Waterfall | Deployment | Build & Release | Manage build | NA | No | Mandatory
105 | AD-Waterfall | Deployment | Build & Release | Develop deployment and support manuals | NA | No | Optional
106 | AD-Waterfall | Deployment | Build & Release Review | Verify delivery | Appraisal | No | Mandatory
107 | AD-Waterfall | Deployment | Build & Release | Package and deliver application | NA | Yes | Mandatory
108 | AD-Waterfall | Deployment | Build & Release Rework | Rework to build plan, build schedule, build scripts based on review comments and defects | Failure | No | Mandatory
109 | AD-Waterfall | User Acceptance Testing | UAT | Setup and verify UAT Test data | Appraisal | No | Optional |  | NA for Independent testing
110 | AD-Waterfall | User Acceptance Testing | UAT | Setup acceptance test environment | Appraisal | No | Optional |  | NA for Independent testing
111 | AD-Waterfall | User Acceptance Testing | UAT | Perform UAT | Appraisal | No | Optional |  | NA for Independent testing
112 | AD-Waterfall | User Acceptance Testing | UAT Sign off | UAT Sign off | NA | No | Optional
113 | AD-Waterfall | User Acceptance Testing | UAT | Perform sanity test for deployment | Appraisal | No | Optional
114 | AD-Waterfall | User Acceptance Testing | UAT Rework | Resolve UAT Defects | Failure | No | Optional |  | NA for Independent testing
115 | AD-Waterfall | User Acceptance Testing | UAT Rework | Support UAT | Failure | No | Optional |  | Test Driven Development
116 | AD-Waterfall | User Acceptance Testing | UAT | Perform sanity test for deployment | Appraisal | No | Optional |  | Test Driven Development
117 | AD-Waterfall | Deployment | Production Rollout | Prepare Production Rollout Plan | NA | No | Optional
118 | AD-Waterfall | Deployment | Production Rollout | Prepare Production Rollback Plan | NA | No | Optional
119 | AD-Waterfall | Deployment | Production Rollout Review | Perform Operational Readiness Review | Appraisal | No | Optional
120 | AD-Waterfall | Deployment | Production Rollout | Perform Production Rollout | NA | No | Optional
121 | AD-Waterfall | Deployment | Production Rollout | Plan Handover | NA | No | Optional
122 | AD-Waterfall | Deployment | Sign off Production Release | Signoff Production Release | NA | No | Optional
123 | AD-Waterfall | Deployment | Warranty Support | Provide post implementation support based on warranty | Failure | No | Optional
124 | AD-Waterfall | Deployment | User Training | User Training activities including planning, training sessions & co-ordination activities | Prevention | No | Optional
125 | AD-Waterfall | Deployment | Defect Prevention Analysis | Defect Prevention Analysis | Prevention | No | Optional
126 | AD-Waterfall | Monitoring & Control | Continual Service Improvement | Monitor CSI theme progress | Prevention | No | Optional
127 | AD-Waterfall | Monitoring & Control | Continual Service Improvement | Validate CSI actual benefits | Prevention | No | Optional
128 | Testing | Test Strategy & Planning | Functional Requirements | Understand business process/ intended application | NA | No | Optional
129 | Testing | Test Strategy & Planning | Functional Requirements | Prepare application inventory | NA | No | Optional
130 | Testing | Test Strategy & Planning | Functional Requirements | Elicit and analyze test requirements | NA | No | Optional
131 | Testing | Test Strategy & Planning | Functional Requirements | Document test requirements | NA | No | Optional
132 | Testing | Test Strategy & Planning | Functional Requirements | Establish test requirements traceability | NA | No | Optional
133 | Testing | Test Strategy & Planning | Functional Requirements Sign off | Sign off test requirements | NA | No | Optional
134 | Testing | Test Strategy & Planning | Functional Requirements | Develop Test strategy for integration, system regression and user acceptance testing | NA | No | Optional
135 | Testing | Test Strategy & Planning | UAT Plan | Develop Acceptance Test Cases | Appraisal | No | Optional
136 | Testing | Test Strategy & Planning | Functional Requirements Sign off | Sign off test requirements | NA | No | Optional
137 | Testing | Test Strategy & Planning | Requirements Review | Review test requirements | Appraisal | No | Optional
138 | Testing | Test Strategy & Planning | Requirements Rework | Rework test requirements | Failure | No | Optional
139 | Testing | Test Strategy & Planning | Test Strategy Review | Review Test strategy | Appraisal | No | Optional
140 | Testing | Test Strategy & Planning | Test Strategy Rework | Rework Test strategy | Failure | No | Optional
141 | Testing | Test Strategy & Planning | UAT Plan Review | Review Acceptance Test Cases | Appraisal | No | Optional
142 | Testing | Test Strategy & Planning | UAT Plan Rework | Rework Acceptance Test Cases | Failure | No | Optional
143 | Testing | Test Design | Integration Test Plan | Develop Integration Test plans, scenarios and cases | Appraisal | No | Optional
144 | Testing | Test Design | Integration Test Plan Review | Review Integration Test plans, scenarios and cases | Appraisal | No | Optional
145 | Testing | Test Design | Integration Test Plan Rework | Rework Integration Test plans, scenarios and cases | Failure | No | Optional
146 | Testing | Test Design | Integration Test Plan | Sign off integration test plans, scenarios and test cases | Appraisal | No | Optional
147 | Testing | Test Design | System Test Plan | Develop system Test plans, scenarios and cases | Appraisal | No | Optional
148 | Testing | Test Design | System Test Plan Review | Review system Test plans, scenarios and cases | Appraisal | No | Optional
149 | Testing | Test Design | System Test Plan Rework | Rework system Test plans, scenarios and cases | Failure | No | Optional
150 | Testing | Test Design | System Test Plan | Sign off system test plans, scenarios and test cases | Appraisal | No | Optional
151 | Testing | Test Design | Regression Test Plan | Develop regression Test suites and cases | Appraisal | No | Optional
152 | Testing | Test Design | Regression Test Plan Review | Review regression Test suites and cases | Appraisal | No | Optional
153 | Testing | Test Design | Regression Test Plan Rework | Rework regression Test suites and cases | Failure | No | Optional
154 | Testing | Test Design | Regression Test Plan | Sign off regression test suites and test cases | Appraisal | No | Optional
155 | Testing | Test Design | Test Environment Setup | Establish traceability of system/ integration/ regression test cases | NA | No | Optional
156 | Testing | Test Design | Test Environment Setup | Prepare test data requirements | NA | No | Optional
157 | Testing | Test Design | Test Environment Setup | Review test data | NA | No | Optional
158 | Testing | Test Design | Test Environment Setup | Rework test data | NA | No | Optional
159 | Testing | Test Design | Test Environment Setup | Configure test environment | NA | No | Optional
160 | Testing | Test Execution | Test Reporting | Compile application performance baselines | NA | No | Optional
161 | Testing | Test Execution | Smoke Testing | Perform smoke testing | Appraisal | No | Optional
162 | Testing | Test Execution | Integration Testing | Perform integration testing | Appraisal | No | Optional
163 | Testing | Test Execution | System Testing | Perform system testing | Appraisal | No | Optional
164 | Testing | Test Execution | Regression Testing | Perform regression testing | Appraisal | No | Optional
165 | Testing | Test Execution | Test Reporting | Prepare test summary report | NA | No | Optional
166 | Testing | Test Execution | Integration Testing Rework | Resolve Integration Testing defects | Failure | No | Optional
166 | Testing | Test Execution | System Testing Rework | Resolve System Testing defects | Failure | No | Optional
167 | Testing | Test Execution | Test Reporting | Sign off testing | NA | No | Optional
168 | Testing | User Acceptance Testing | UAT | Setup and verify UAT Test data | Appraisal | No | Optional
169 | Testing | User Acceptance Testing | UAT | Setup acceptance test environment | Appraisal | No | Optional
170 | Testing | User Acceptance Testing | UAT | Perform UAT | Appraisal | No | Optional
171 | Testing | User Acceptance Testing | UAT Rework | Resolve UAT Defects | Failure | No | Optional
172 | Testing | User Acceptance Testing | UAT Sign off | UAT Sign Off | NA | No | Optional
173 | Project Management | Project Planning | Project Initiation | Initiate Project | NA | No | Mandatory
174 | Project Management | Project Planning | Project Set up | Setup Project | NA | No | Mandatory
175 | Project Management | Project Planning | Project Planning | Determine Project's lifecycle phases | NA | No | Mandatory
176 | Project Management | Project Planning | Project Planning | Establish Project's method and process | NA | No | Mandatory
177 | Project Management | Project Planning | Metrics & Goal Setting | Establish Project's KPI and Metrics Plan | NA | No | Mandatory
178 | Project Management | Project Planning | Project Estimation | Establish Estimates for the Project | NA | No | Mandatory |  | Co - Managed, MS
179 | Project Management | Project Planning | Project Scheduling | Develop Project Schedule | NA | No | Mandatory
180 | Project Management | Project Planning | Project Planning | Establish Configuration Management System | NA | No | Mandatory
181 | Project Management | Project Planning | BCM Planning | Establish BCP | NA | No | Mandatory
182 | Project Management | Project Planning | Project Planning | Plan Project Resources | NA | No | Mandatory
183 | Project Management | Project Planning | Independent Testing Plan | Plan for QA | NA | No | Mandatory
184 | Project Management | Project Planning | Project Planning | Assess and Identify Risks | NA | No | Mandatory
185 | Project Management | Project Planning | Project Planning | Plan for necessary trainings and skills | NA | No | Mandatory |  | Co - Managed, MS
186 | Project Management | Project Planning | Schedule Review | Review Project Schedule | Appraisal | No | Mandatory
187 | Project Management | Project Planning | Schedule Rework | Rework Project Schedule | Failure | No | Mandatory
188 | Project Management | Project Planning | Develop Project Management Plan | Develop Project Management Plan | NA | No | Mandatory
189 | Project Management | Project Planning | Review Project Management Plan | Review and Approve Project Management Plan | Appraisal | No | Mandatory
190 | Project Management | Project Planning | Project Planning | Update plan for integration with related application/ projects under Cognizant | NA | No | Mandatory |  | MS
191 | Project Management | Project Planning | Project Planning | Identify CSI core team | NA | No | Optional |  | Continual Service Improvement
192 | Project Management | Project Planning | Project Planning | Identify themes to address pain areas/ opportunities | NA | No | Optional |  | Continual Service Improvement
193 | Project Management | Project Planning | Project Planning | Review and approve themes by key stakeholders & Customer | NA | No | Optional |  | Continual Service Improvement
194 | Project Management | Project Planning | Project Planning | Identify solution approach | NA | No | Optional |  | Continual Service Improvement
195 | Project Management | Project Planning | Project Planning | Create CSI execution plan | NA | No | Optional |  | Continual Service Improvement
196 | Project Management | Project Planning | Project Planning | Review and approve CSI execution plan | NA | No | Optional |  | Continual Service Improvement
197 | Project Management | Execution | Monitoring and Control | Monitor project against plan | NA | No | Mandatory
198 | Project Management | Execution | Planning and Tracking CAPA | Manage corrective actions | NA | No | Mandatory
199 | Project Management | Execution | Quantitative Project Management | Perform Quantitative Project Management | NA | No | Mandatory |  | Co- Managed, MS
200 | Project Management | Execution | Risk Monitoring and Control | Perform risk management | NA | No | Mandatory
201 | Project Management | Execution | Defect Prevention Analysis | Perform defect and problem prevention | Prevention | No | Mandatory |  | Co- Managed, MS
202 | Project Management | Execution | Quality and Audit Related Activities | Perform Delivery Excellence activities | NA | No | Mandatory
203 | Project Management | Execution | Monitoring and Control | Perform coordination with related projects | NA | No | Mandatory |  | MS
204 | Project Management | Execution | Project Review | Perform Project Management reviews | Appraisal | No | Mandatory |  | MS
205 | Project Management | Execution | Account Review | Perform Account Management Reviews | Appraisal | No | Mandatory |  | MS
206 | Project Management | Execution | Monitoring and Control | Perform Integrated Governance meetings | NA | No | Mandatory |  | MS
207 | Project Management | Execution | Monitoring and Control | Perform Steering committee meetings | NA | No | Mandatory |  | MS
208 | Project Management | Execution | Monitoring and Control | Perform Change Management | NA | No | Mandatory
209 | Miscellaneous | Miscellaneous | Miscellaneous | Miscellaneous | NA | No