## Workpackage Milestone Details
Mark Task as Milestone | ID | Phase | Standard Code | Name | Overall Status | Planned Finish | Baseline Finish | Actual Finish
Y | WPKG34_TSK13 | Migration Readiness and Plan | Cloud Readiness Assessment | Perform Cloud Readiness Assessment | Closed | 28-Nov-2019 | 29-Nov-2019 | 28-Nov-2019
Y | WPKG34_TSK16 | Migration Readiness and Plan | Cloud Readiness Assessment Sign-Off | Obtain Cloud Readiness Assessment Sign-off | Closed | 28-Nov-2019 | 29-Nov-2019 | 28-Nov-2019
Y | WPKG34_TSK18 | Migration Readiness and Plan | Business Case | Define High Level Business Case | Closed | 28-Nov-2019 | 29-Nov-2019 | 28-Nov-2019
Y | WPKG34_TSK21 | Migration Readiness and Plan | Business Case Sign-Off | Sign-off Business Case | Closed | 28-Nov-2019 | 29-Nov-2019 | 28-Nov-2019
Y | WPKG34_TSK32 | Design and Build | Cloud Deployment | Develop Cloud Deployment Architecture | Closed | 28-Nov-2019 | 29-Nov-2019 | 28-Nov-2019
Y | WPKG34_TSK37 | Design and Build | Cloud Deployment Signoff | Task added manually in Linked Task | Closed | 28-Nov-2019 | 29-Nov-2019 | 28-Nov-2019

## Milestone e-form Details
ID | Name | Status | Actual Milestone End Date | Milestone Due Date | Scope of Milestone
MLS146 | WPKG34 - Task added manually in Linked Task | Completed | 28-Nov-2019 | 29-Nov-2019 | Extra
MLS145 | WPKG34 - Develop Cloud Deployment Architecture | Completed | 28-Nov-2019 | 29-Nov-2019 | Extra
MLS144 | WPKG34 - Sign-off Business Case | Completed | 28-Nov-2019 | 29-Nov-2019 | Extra
MLS143 | WPKG34 - Define High Level Business Case | Completed | 28-Nov-2019 | 29-Nov-2019 | Extra
MLS142 | WPKG34 - Obtain Cloud Readiness Assessment Sign-off | Completed | 28-Nov-2019 | 29-Nov-2019 | Extra
MLS141 | WPKG34 - Perform Cloud Readiness Assessment | Completed | 28-Nov-2019 | 29-Nov-2019 | Extra